## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
Project Charter - Goku Black
Goku Black |  |  |  |  | Legend: |  | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Brenden
Project Start Date: | 2024-02-19 | [5 empty] | February | [13 empty] | March | [27 empty] | April | [29 empty] | May
Scrolling Increment: | 0 | time axis 2024-02-19 to 2024-05-31
Milestone description | Category | Assigned to | Progress | Start | Days | Column1 | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Iteration 1
Improve collaboration and communication | Goal | Group | 100% | 2024-02-19 | 27 |  | 2024-02-19: 2; 2024-02-20: 2; 2024-02-21: 2; 2024-02-22: 2; 2024-02-23: 2; 2024-02-24: 2; 2024-02-25: 2; 2024-02-26: 2; 2024-02-27: 2; 2024-02-28: 2; 2024-02-29: 2; 2024-03-01: 2; 2024-03-02: 2; 2024-03-03: 2; 2024-03-04: 2; 2024-03-05: 2; 2024-03-06: 2; 2024-03-07: 2; 2024-03-08: 2; 2024-03-09: 2; 2024-03-10: 2; 2024-03-11: 2; 2024-03-12: 2; 2024-03-13: 2; 2024-03-14: 2; 2024-03-15: 2; 2024-03-16: 2
Building persona | Low Risk | James, Noah | 100% | 2024-02-22 | 3
Testing the personas | Low Risk | Brenden | 100% | 2024-03-03 | 10
Submit personas | Milestone | Noah,Brenden, James | 100% | 2024-03-04 | 1 | bar: 2024-03-04
Review and recap | On Track | Noah,Brenden, James | 100% | 2024-03-10 | 6
Complete stakeholder register | Low Risk | Brenden, James | 100% | 2024-03-13 | 2
Test the stakeholder register | Med Risk | Noah,James | 100% | 2024-03-15 | 2 | bar: 2024-03-15 to 2024-03-17
Hand everything in and submit. | Milestone | Group | 100% | 2024-03-25 | 1 | bar: 2024-03-25
Iteration 2
Planning meeting report | Milestone | Group | 100% | 2024-01-04 | 1 | bar: 2024-04-01
Complete resource needs | Low Risk | Brenden, James | 100% | 2024-11-04 | 3 | bar: 2024-04-11 to 2024-04-13
Improve communication goal | Goal | Group | 100% | 15/4/2024 | 6
Update github board (Completed issues ect) | Low Risk | Noah | 100% | 20/4/2024 | 2 | bar: 2024-04-20 to 2024-04-21
Record any issues in github issues | On Track | Brenden | 100% | 21/4/2024 | 10 | bar: 2024-04-21 to 2024-04-30
Readme.md documentation GitHub | Low Risk | Group | 100% | 25/4/2024 | 5 | bar: 2024-04-25 to 2024-04-29
Complete Iteration 2 and hand in. | Milestone | Group | 100% | 2024-01-05 | 1 | bar: 2024-05-01
Iteration 3
Planning meeting report | Milestone | Group | 100% | 2024-05-10 | 1 | bar: 2024-05-10
Complete risk register | Goal | James | 100% | 2024-05-19 | 3
Update the github board | Low Risk | Noah | 100% | 2024-05-17 | 6 | bar: 2024-05-17 to 2024-05-22
Record any issues we come across in github issues. | On Track | Group | 100% | 2024-05-10 | 14 | bar: 2024-05-10 to 2024-05-24
Improve work ethics | On Track | Group | 100% | 2024-05-10 | 14 | bar: 2024-05-10 to 2024-05-24
Further update github readme.md | Low Risk | Noah | 100% | 2024-05-21 | 2 | bar: 2024-05-21 to 2024-05-22
Complete Iteration 3 and hand in. | Milestone | Group | 100% | 2024-05-24 | 1 | bar: 2024-05-24
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-05-24 |  |  |  |  | May | [13 empty] | June | [27 empty] | July
Scrolling Increment: | 0 | time axis 2024-05-24 to 2024-07-18
Milestone description | Category | Assigned to | Progress | Start | Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
Iteration 1
Impreove collaboration and communication | Goal | Name | 25% | 2024-03-19 | 3
Building persona | Milestone | James, Noah,Brenden |  | 2024-05-29 | 1 | bar: W
Testing persona | Low Risk | Noah,Brenden, James | 50% | 2024-03-16 | 10
Task 4 | Milestone |  |  | 2024-04-08 | 1
Task 5 | Med Risk |  | 10% | 2024-03-25 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-03-25 | 13
Task 2 | On Track |  | 50% | 2024-03-27 | 9
Task 3 | Low Risk |  | 33% | 2024-04-01 | 11
Task 4 | Milestone |  |  | 2024-04-03 | 1
Task 5 |  |  |  | 2024-04-04 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-04-03 | 4
Task 2 | Med Risk |  |  | 2024-04-06 | 14
Task 3 | On Track |  |  | 2024-04-21 | 6
Task 4 | Goal |  |  | 2024-04-25 | 3
Task 5 | Low Risk |  |  | 2024-03-25 | 19
TITLE 4
Task 1 |  |  |  | 2024-04-28 | 15
Task 2 |  |  |  | 2024-05-12 | 5
Task 3 | Milestone |  |  | 2024-06-23 | 1 | bar: S
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2024-05-24 |  |  |  |  | May | [6 empty] | June | [27 empty] | July
Scrolling Increment: | 5 | time axis 2024-05-29 to 2024-07-23
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-05-29 to 2024-07-23
TITLE 1
Task 1 | Goal | Name | 25% | 2024-05-24 | 3
Task 2 | Milestone |  |  | 2024-05-29 | 1 | bar: 2024-05-29
Task 3 | Low Risk |  | 50% | 2024-05-21 | 10
Task 4 | Milestone |  |  | 2024-06-13 | 1 | bar: 2024-06-13
Task 5 | Med Risk |  | 10% | 2024-05-30 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2024-05-30 | 13
Task 2 | On Track |  | 50% | 2024-06-01 | 9
Task 3 | Low Risk |  | 33% | 2024-06-06 | 11
Task 4 | Milestone |  |  | 2024-06-08 | 1 | bar: 2024-06-08
Task 5 |  |  |  | 2024-06-09 | 24
TITLE 3
Task 1 | On Track |  |  | 2024-06-08 | 4
Task 2 | Med Risk |  |  | 2024-06-11 | 14
Task 3 | On Track |  |  | 2024-06-26 | 6
Task 4 | Goal |  |  | 2024-06-30 | 3 | 2024-06-30: 2; 2024-07-01: 2; 2024-07-02: 2
Task 5 | Low Risk |  |  | 2024-05-30 | 19
TITLE 4
Task 1 |  |  |  | 2024-07-03 | 15
Task 2 |  |  |  | 2024-07-17 | 5
Task 3 | Milestone |  |  | 2024-08-28 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one